## Timeline
S# | Day | Date | Task
1 | Day 1 | 2020-06-10 | Wireframe only as per toolchain/features assigned to respective SME
2 | Day 1 | 2020-06-10 | Fill Technical Analysis File and get it reviewed internally ¦ Need to update the technical analysis file as per the use cases/toolchain respective SME is working
3 | Day 2 | 2020-06-11 | Starting working on code template and test cases
4 | Day 2 | 2020-06-11 | Daily review of progress for 3
5 | Day 2/3 | 2020-06-12 | Configure the test cases as per Yaksha convention
6 | Day 2/3/4 | 2020-06-13 | Review of configuration
7 | Day 5 | 2020-06-15 | Commit to github
8 | Day 5 | 2020-06-15 | Test links creation
9 | Day 5 | 2020-06-15 | Report generation